## Sheet1
Completion Report on the Use of GEF Hanoi Urban Transport Development Project (P085393) Preparation Grants as of May 17, 2007
1. Please find the Completion Report for the above mentioned PDF Block B Grant (TF053047) which was approved on April 20, 2004 with a funding of Three Hundred Fifty Thousand US Dollars (US$350,000) executed by the recipient.
2. The recipient has successfully completed most of the activities funded under the PDF Block B, and the outputs are satisfactory. The specific activities funded under the PDF Block B are listed in the following table. A summary of the outputs is included. All uncommitted funds for activities that were not completed will be refunded to GEF.
Approved |  |  |  | Actuals
Proposed Activities at Approval |  | GEF financing | Co-financing | Completed Activities |  | GEF Financing committed | Cofinancing committed | Uncommitted GEF funds
Component 1 - Buses |  | 120000 | 0 | Busways Feasibility Study |  | 30000 | 470000 | 80000
Component 2 – Study Tour |  | 50000 | 0 | Study Tour |  | 60000 | 25000
Component 3 – Busways Outreach |  | 50000 | 0 | Focus groups, press coverage, strategy |  | 7352 | 30000 | 22648
Component 4 – Non-motorized |  | 50000 | 0 | Feasability Study of works and actions for enhancing NMT access to BRT based on analysis, and travel surveys and interviews |  | 33000 | 0 | 0
Component 5 Integrated Sustainable Urban Development (Transport + Land Use) |  | 30000 | 0 | Feasability Stiudy report on activities and actions to integrate land-use and transport planning in Hanoi |  | 110000 | 0
Component 6 - Implementation |  | 50000 | 0 | Workshops, detailed monitoring plan, a project implementation plan and completed audits |  | 0 | 50000 | 7000
Total |  | 350000 | 0 | Total |  | 240352 | 575000 | 109648
The total amount of uncommitted funds to be returned to GEF is US$109,648.
Note on activities conducted and role of other co-financing. The PDF-B grant was being co-financed with other funds including PHRD grant funds (which financed much of the BRT feasibility, the implementation plans, and the BRT outreach), some parallel actions financed by EU agencies (who contributed to the Study Tour) and tHanoi itself (who financed all operating costs and many of the workshops). The availability of adequate other funds limited the amount of GEF funds used for BRT preparation. At the same time, during preparation a champion emerged in the Planning and Management unit of Hanoi who was interested in compact city development. As a result the money spent on the land-use transport integration agenda was increased significantly. Finally monies were left either undisbursed or uncommitted - all because of the difficulties of contracting and disbursing funds in Vietnam - a significant transaction cost associated with working there.
Project Preparation Grant Management Budget
| Approved |  |  | Committed
| Staff weeks | GEF Financing | Co-financing | Staff weeks | GEF Financing | Co-financing
Personnel
Local Consultants |  |  | 0 | 326 | 50000 | 113000
International Consultants |  |  | 0 | 149.8667 | 130000 | 432000
Training |  |  | 0 |  | 0
Office Equipment |  |  | 0 |  | 0
Travel |  |  | 0 |  | 60000 | 25000
Miscellaneous |  |  | 0 |  | 352 | 5000
Total |  |  | 0 |  | 240352 | 575000
Outputs from completed project preparation activities
Specific outputs of the PDF-B included a completed and approved feasibility study for the BRT, a report on integrated transport and urban planning including recommendations for a GEF component, a report on enhancing NMT access to the BRT system including reports on focus group/survey results, options for increasing pedestrianization in the central city and a recommended plan of specific works for GEF consideration to increase NMT access to the BRT and a report of the Study Tour to Latin America (Hanoi PC formally approved the BRT concept based on this report). All the reports are on file. The GEF components of HUTDP were prepared as a result of the outputs of the GEF PDF-B grant.

## Sheet2
Component/ Subcomponent | GEF Budget | Goods | Works | Non-Consultant Services | Consultant Services | Procurement Method | Date of RFP | Date of award | Indicative completion/delivery date
Component 1 - Buses
Busways Feasibility Study | 120000 |  |  |  |  | QCBS | 2004-05-15 | 2004-12-15 | 2005-10-15
Component 2 – Study Tour
Study Tour | 50000 |  |  | 50000 |  | Shopping | 2004-05-15 | 2004-12-15 | 2005-10-15
Component 3 – Busways Outreach
Define Focus Group Surveys | 10000 |  |  |  | 10000 | IC (SS) | 2004-05-15 | 2004-12-15 | 2005-10-15
Focus Groups I | 5000 |  |  |  | 5000 | Fixed Cost | 2004-05-15 | 2004-12-15 | 2005-10-15
Focus Groups II | 10000 |  |  |  | 10000 | Fixed Cost | 2004-05-15 | 2004-12-15 | 2005-10-15
Design Outreach Program for main GEF grant | 25000 |  |  |  | 25000 | CQ | 2004-05-15 | 2004-12-15 | 2005-10-15
Component 4 – Non-motorized
Define approach and identify champions for walking and cycling | 10000 |  |  |  | 10000 | IC (SS) | 2004-05-15 | 2004-12-15 | 2005-10-15
Travel and focus group surveys | 20000 |  |  |  | 20000 | Fixed Cost | 2004-05-15 | 2004-12-15 | 2005-10-15
Design Non-Motorized Transport Program for main GEF grant | 20000 |  |  |  | 20000 | CQ | 2004-05-15 | 2004-12-15 | 2005-10-15
Component 5 – Integrated Sustainable Urban Development (Transport + Land Use)
Review planning practices and legal framework . Identify opportunities for better integration | 10000 |  |  |  | 10000 | IC (SS) | 2004-05-15 | 2004-12-15 | 2005-10-15
Design Technical Assistance Program for main GEF grant | 20000 |  |  |  | 20000 | IC (CVs) | 2004-05-15 | 2004-12-15 | 2005-10-15
Component 6 – Implementation
Workshops | 10000 |  |  | 10000 |  | Shopping | 2004-05-15 | 2004-12-15 | 2005-10-15
Design monitoring plan for main GEF grant | 10000 |  |  |  | 10000 | IC (CVs) | 2004-05-15 | 2004-12-15 | 2005-10-15
Implementation Plan | 10000 |  |  |  | 10000 | IC (CVs) | 2004-05-15 | 2004-12-15 | 2005-10-15
Operating Costs | 10000 | 2000 |  | 8000 |  | Shopping | 2004-05-15 | 2004-12-15 | 2005-10-15
Audits | 10000 |  |  |  | 10000 | Least Cost | 2004-05-15 | 2004-12-15 | 2005-10-15
TOTAL | 350000