ProGRAM Identification Form (PIF)

Project Type:

the GEF Trust Fund

Submission Date:

Re-submission Date:  02/11/2008

| part i: project IDentification Indicative Calendar |  |
| --- | --- |
| Milestones | Expected Dates |
| Work Program (for FSP) | April 2008 |
| CEO Endorsement/Approval |  |
| GEF Agency Approval | June 2009 |
| Implementation Start | August 2009 |
| Mid-term Review (if planned) | Feb 2012 |
| Implementation Completion |  |

GEFSEC Project ID: 2762

gef agency Project ID:

Country(ies): Vietnam

Project Title:  Country Program Framework for Sustainable Management

GEF Agency(ies): , IFAD, UNDP

Other Executing partner(s): Department of Forestry,

GEF Focal Area (s): , Biodiversity, Climate Change

GEF-4 Strategic program(S): SLM SO2 -

Name of parent program/umbrella project:  NA

- Project framework  (Expand table as necessary)

| Project Objective: |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ### Project Components | ### Indicate whether Investment, TA, or STA** | Expected Outcomes | ### Expected Outputs | ### Indicative GEF Financing* |  | Indicative Co-financing* |  | Total ($) |
|  |  |  |  | ### ($) | ### % | ### ($) | ### % |  |
| 1. Sustainable forest and forest land management | Investment + STA | Increased area of forest and forest land managed in a sustainable manner as part of the wider landscape, with biodiversity conservation benefits, and contributing to climate change adaptation and mitigation | Areas (hectares) for which participatory SFLM practices have been defined in land use/management plans. Areas (hectares) for which SFLM agreements and participatory investment plans with households, communities or institutions have been signed. Areas (hectares) for which biodiversity conservation measures are defined. Areas (hectares) for which payments for environmental services are in place. | 1.5 | 1% | 185 | 99% | 186.5 |
| 2. Increased capacity to apply sustainable forest land management methods |  | Increased capacity of institutions to: (a) support land users to invest in sustainable forest land management, and (b) effective monitoring and control of destructive practices | Curriculum development and number of staff trained and employed at provincial and lower level staff in sustainable forest management, Improved monitoring mechanisms to control destructive practices, forest destruction and illegal logging, and monitor biodiversity conservation activities | 2.5 | 9% | 24 | 91% | 26.5 |
| 3. Institutional strengthening and policy development | Investment and TA | Increased institutional capacity to manage policy research and develop sustainable natural resource management policy/regulatory frameworks Forest –related policy and regulatory frameworks incorporate biodiversity concerns for production forests | Clear and consistent legislation and regulations in environment, forestry and land management sub-sectors Key studies resulting in policies and legislation in support of SFLM Consistent policy, fiscal and financial framework for forestry sector including biodiversity conservation measures | 1.5 | 8% | 18 | 92% | 19.5 |
| 4. Program Coordination/Management |  | Collaborative support for SFLM according to agreed program objectives | No. of program framework agreements signed Regular dialogue on SFLM policy implemented | 0.387 | 16% | 2 | 84% | 2.387 |
| Total project costs |  |  |  | 5.887 | 2.5% | 229 | 97.5% | 234.887 |

*   List the $ by project components.  The percentage is the share of GEF and Co-financing respectively to the total amount for the component.

** TA = Technical Assistance;  STA = Scientific & technical analysis.

B.   Indicative Financing Plan Summary For The Project ($)

|  | Project Preparation* | Project | Agency Fee | Total |
| --- | --- | --- | --- | --- |
| GEF | 550,000 | 5,886,550 | 643,450 | 7,080,000 |
| Co-financing | 1,033,650 | 229,000,000 |  | 230,033.650 |
| Total | 1,583,650 | 234,886,550 | 643,450 | 237,113,650 |

*   Please include the previously approved PDFs and planned request for new PPG, if any.  Indicate the amount already approved as 
            footnote here and if the GEF funding is from GEF-3.

C.   Indicative Co-financing for the project (including project preparation amount) by source and
       by name  (in parenthesis) if available, ($)

| Sources of Co-financing | Type of Co-financing | Amount |
| --- | --- | --- |
| Project Government Contribution | In-kind/Budget | 35,000,000 |
| GEF Agency(ies) | Soft Loan (WB/IFAD) Grant (UNDP) | 34,000,000 700,000 |
| Bilateral Aid Agency(ies) | Grant Soft loan | 54,300,000 40,000,000 |
| Multilateral Agency(ies) | Soft Loan (ADB) | 45,000,000 |
| Private Sector | Unknown at this Stage |  |
| NGO | Unknown at this Stage |  |
| Others | Beneficiaries | 20,000,000 |
| Total co-financing |  | 229,000,000 |

D.   GEF Resources Requested by Focal Area(s), agency (ies) share and country(ies)*

| GEF Agency | Focal Area | Country Name/ Global | (in $) |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Project Preparation | Project | Agency Fee | Total |
| World Bank | Biodiversity | Vietnam/ RAF-4 | 350,000 | 3,286,000 | 364,000 | 4,000,000 |
| World Bank | Land Degradation | GEF Global |  | 909,000 | 91,000 | 1,000,000 |
| UNDP | Climate change | Vietnam/ RAF-4 | 100,000 | 810,000 | 90,000 | 1,000,000 |
| UNDP | Land degradation | GEF Global |  | 227,000 | 23,000 | 250,000 |
| IFAD | Land degradation | GEF Global | 20,000 | 130,910 | 15,090 | 166,000 |
| IFAD | Biodiversity | Vietnam/ RAF-4 | 80,000 | 523,640 | 60,360 |  |
| Total GEF Resources |  |  | 550,000 | 5,886,550 | 643,450 | 7,080,000 |

*  No need to provide information for this table if it is a single focal area, single country and single GEF Agency project.

part ii:  project JustiFication

State the issue, how the project seeks to address it, and the expected global environmental benefits to be delivered:

- Describe the consistency of the project with national priorities/plans:  Vietnam is a signatory to the UNCCD, CBD and UNFCCC.  The proposed CPFSFLM Program is consistent with the national Socio-economic Development Plan 2006-2010, the Strategic Orientation for Sustainable Development in Vietnam (Vietnam’s Agenda 21), the Vietnam Environment Protection Strategy and the Vietnam Forestry Development Strategy (FDS) and Vision 2020.  SFM is one of the five priority program areas of the FDS.  The program also complies with the National Biodiversity Strategy and Action Plan (1995) which includes conservation needs outside protected areas, the National Environmental Action Plan 2001-2010, and the UNCCD National Action Plan 2006-2010 (NAP) which sets out short, medium and long term actions for addressing land degradation through sustainable forest land management.  A forthcoming Law on Biodiversity will also address issues of biodiversity conservation in production forest landscapes which is consistent with project objectives.

Recent reforms of State Forest Enterprises and reclassification of forestland has meant that large amounts of forest land is being/will be released for productive or protection purposes.  However, the government recognizes that institutional reform and subsequent forest land use planning and allocation will be a costly process and substantial investments will be required if forestland management practices are to become sustainable in the longer term.  The Annual Reports of UNCCD Implementation have identified the need to address the causes of land degradation and to rehabilitate and restore the production capacity of degraded areas.  The Government has recently enacted new legislation that provides a supporting framework for the proposed Project including the Land Law 2003, Law on Forest Protection and Development 2004, and Environment Protection Law 2005.  The UNCCD provides an ideal framework for coordinating work between MARD and MONRE, the two agencies responsible for land and forest management; a National Coordinating Body (NCB) has been established for the coordination of actions under the NAP and is tasked to develop the proposed program.

- Describe the consistency of the project with gef strategies and strategic programs:  The program is consistent with the GEF’s Framework Strategy for Sustainable Forest Management for GEF-4 (25 July 2007) through its support for reversing the loss of forest cover through sustainable forest management, including protection, restoration, afforestation and reforestation, and increasing efforts to prevent forest degradation; and to enhance forest-based economic, social and environmental benefits, including by improving the livelihoods of forest-dependent people.  It is also consistent with Land Degradation OP15 through its intention to arrest and reverse current trends in land degradation and with both LD-SO1 to develop an enabling environment for SLM in the main stream of development policy and practice at regional, national and local levels, and LD-SO2 to promote mutual benefits for the global environment and local livelihoods by catalyzing SLM investments to replicate successful practices. This will be accomplished through institutional capacity building and policy development as well as direct investment in the expanding of forest land use planning and forest land allocation measures, as well as facilitating complementary investment in replicating improved land management methods through a multi-donor program partnership approach.  The CPPFSLM will support policies and practices conducive to SLM that, simultaneously, generate global environmental benefits while supporting local and national, social and economic development. Program actions will contribute to national programs in the field of natural resources management, including sustainable forest management.  The proposed Program supports both Strategic Objectives of the Sustainable Forest Management Framework Strategy as follows: Under SFM SO2 - LD-SP2 by supporting landscape approaches to the management of woodlands, humid forest margins and reducing forest fragmentation by; a) strengthening the enabling policy and institutional environment for managing forests in the wider landscape; b) defining strategies to avoid the degradation of woodlands, forest margins and further forest fragmentation; and c) replicating successful practices in SFM in the wider landscape to restore the integrity of forest ecosystems: BD-SP4 by removing critical knowledge barriers, developing institutional capacities, and establishing the forest policies, legislative and regulatory frameworks required to integrate sustainable use objectives into the forest sector; BD-SP5 by a) increasing country capacity to scale up and increase the sustainability of forest certification systems and b) supporting the design and implementation of payment for environmental service (PES) schemes to compensate forest resource managers for off-site ecological benefits; and under SFM SO1 CC-SP6 by assessing the potential in Vietnam to develop methods to promote the reduction of greenhouse gas (GHG) emissions from land use, land use change and forestry (LULUCF).  The policy development sub-component will build on lessons from existing pilot programs for PES in Vietnam to establish methodologies to reliably measure carbon stored/emitted from LULUCF and test systems and practices that reduce emissions, increase sequestration, and accurately measure and monitor the benefits of such efforts in the forest sector.

- Outline the Coordination with other related initiatives: The proposed Program is being developed under the UNCCD Secretariat which comprises of relevant government agencies to ensure coordination among different agencies of the government.  The development of the proposed Program is being co-financed by the Trust Fund for Forests under management of the Forest Sector Support Program and Partnership which represents 26 donor signatories including the World Bank, UNDP, Asian Development Bank, FAO and means that key partners have reviewed and endorsed the project concept. Donors including IFAD, ADB, IFAD, KfW, GTZ, JICA and European Commission are preparing or implementing projects and programs with complementary objectives under the umbrella of CPFSFLM.  Both IFAD and UNDP are proposing GEF funded projects under the umbrella of the CPFSFLM and actively participated in a joint workshop in Hanoi in January to approve the CPFSFLM GEF submission (Annex 1). A GEF supported project entitled “Strengthening Sustainable Management of the Protection Area System in Vietnam” will be implemented by the Vietnam Environmental Protection Agency. The CPFSFLM will support the objectives of this project by improving the livelihoods of local communities living near the PAs and reducing the pressure on the PA systems. In addition, a GEF-IFAD regional/multi-country project entitled “Rehabilitation and Sustainable Use of Peatland Forests in South-East Asia” is currently under preparation. NGOs including IUCN, WWF and Oxfam are implementing projects related to demonstration of PES and promotion of market oriented forest industries with community linkages.   The consultations and discussions are continuing as the Program for Sustainable Forest Land Management develops to ensure that is does not overlap with and, to the extent possible, is supported by other related donor initiatives.

- Discuss the vAlue-added of GEF involvement in the project  demonstrated through incremental reasoning :    Without GEF support, poor integration between environment, land and forest management programs will continue to result in a high proportion of under-utilized forestry land and accelerated forest and forest land degradation. Under-investment in production forests will continue to result in a high proportion of unsustainable forest management.  Government forest management plans and policies do not currently emphasize the role of production or protection forests for biodiversity conservation  The incremental value of GEF support to the Project and activities will include: improved knowledge of the underlying causes of forest degradation; identification of lessons from past experience of sustainable forest management approaches; strengthening of methodological approaches, inter-institutional arrangements and capacity; identification and design of sustainable forest management pilots (GoV has identified 4 priority areas for tackling forest degradation and is committed to support provincial authorities in these areas under the NAP). GEF support will build the critical capacity and institutional collaboration mechanisms needed to improve the quality of forest land use planning and allocation processes, introduce biodiversity conservation measures into policies, regulations and plans affecting production and protection forests, provide support for expanding biodiversity conservation in production forest landscapes, and help scale-up successful approaches that take advantage of revised legal frameworks for the environment, water resources, land and forests. Expected incremental global environmental benefits include reduced land degradation processes in the program area, preservation and improvement of the ecosystem functions and services, including climate and water regulation, and soil conservation. Land and forest use will be enhanced sustainably through the use of combined SLM and SFM techniques, helping to improve livelihoods and offer more opportunities for income generation in a durable way; global biodiversity benefits accrued from the conservation and sustainable use of indigenous biodiversity through the application of SFM techniques, the demonstration and application of new economic instruments for environmental management such as PES and forest certification, and the reinforcement of local capacities for monitoring and control of forest conservation; and climate change, benefits from reduced emissions of greenhouse gases through the promotion of efficient and sustainable practices of energy production from biomass, and carbon sequestration. Forest protection, natural regeneration, plantation of protection forest and special use forest, plantation of short-term production forest, plantation of long-term production forest and planting scattered trees have great GHG emission mitigation potential.  The program will support a multi-sector CPFSFLM stakeholder forum and maintain close links with the existing FSSP&P partnership and its SMF working group.

- Indicate risks, including climate change risks, that might prevent the project objective(s) from being achieved, and if possible including risk measures that will be  taken:

Governance: Weak coordination within and between government agencies responsible for forest and land management, together with limited capacity especially at lower levels to interact with land users on the development and management of forestry, are potential barriers to the achievement of program objectives.  The program will emphasize and support improved institutional coordination, capacity building and awareness raising at national level and in Priority Areas.

Institutions: Inconsistency between national legislation, provincial regulations and district implementation guidelines may contribute to ineffective program implementation.  The program will support harmonization of relevant legislation/ regulations.

Climate change: The exposed central coast of Vietnam is subject to risk of increased storm hazards.  This will be managed by increasing area and quality of forest cover to reduce storm and flood damage.

Lack of willingness among donors to collaborate and thus sacrifice potential cost-effectiveness and policy dialogue opportunities.  The CPFSFLM provides a forum for stakeholder consultation on policy, program design and exchange of lessons learned.  The forum is closely linked with the SFM working group of the Forest Sector Support Program.  This risk of weak coordination is considered low.

- describe, if possible, the expected cost-effectiveness of the project:  part of the protect preparation process Not available at this time.  The programmatic approach which involves coordination and collaboration with other GEF and non-GEF entities in the implementation of this program will result in harmonization of approaches and lead to more cost effective investment. During project preparation individual projects under the CPFSFLM program will prepare a cost-effectiveness analysis or assessment based on (i) quantitative approach or (ii) qualitative approach.  If appropriate this analysis will be supplemented by a description of alternate project approaches considered and discarded.

- Justify the comparative advantage of GEF agency:

part iii:  approval/endorsement by gef operational focal point(s) and GEF agency(ies)

A.   Record of Endorsement of GEF Operational Focal Point (S) on Behalf of the Government(S): (Please attach the  country endorsement letter(s)  or regional endorsement letter(s) with this template).

| Dr. Nguyen Van Tai GEF Operational Focal Point Deputy Director General Department of Environment Ministry of Natural Resources and Environment | Date: |
| --- | --- |

| (Enter Name, Position, Ministry) | Date: (Month, day, year) |
| --- | --- |

B.  GEF Agency(ies) Certification

| This request has been prepared in accordance with GEF policies and procedures and meets the GEF criteria for project identification and preparation. |  |
| --- | --- |
| Steve Gorman GEF Agency Coordinator | Mahesh Sharma Project Contact Person |
| Date: | Tel. and Email: (202) 458-7339; msharma@worldbank.org |

Annex 1: Proposed Projects under the GEF-supported Program

| Brief Project Profile and Implementing Agency | Global and Local Environmental Benefits | Expected GEF Contribution | Expected Co-financing | Expected Date of PIF Submission |
| --- | --- | --- | --- | --- |
| Sustainable Forest Land Management Project World Bank The objective of this project is to enable land users to benefit equitably from sustainable forest land management and provide local and global environmental benefits. The project is focused on the central coast (and particularly the north central coast) of Vietnam for the specific purpose of addressing biodiversity conservation issues associated with the substantial areas of natural forest remaining in this area. | The proposed Project will make an important contribution to sustainable management of forests to achieve global environmental benefits (biodiversity conservation, reduced GHG emissions from reduced deforestation, and incremental carbon sequestration), and also enhance local forest-based economic, social and environmental benefits, foster new markets for environmental services, and improve the livelihoods of forest-dependent people. | $5million (LD FA: 1million; BD FA: 4million) | $50million | April 2008 |
| UNDP The objective of this project is | The project will produce local and global environmental benefits within the context of sustainable development and poverty reduction through restoration of regulating ecosystem services, such as water and soil retention, and carbon sequestration, as well as provisioning services, such as habitat, food and water provision. Knowledge generated by the project will be shared nationally and the project will inform international learning on SFM and land degradation. | 1.25million (LD FA: 0.25million; CC FA: 1million) | 5million | Tbd |
| Promotion of Sustainable Forest and Land Management in the Vietnam Uplands IFAD The objective of this project is to preserve forest resources and reduce land degradation, through the application of sustainable forest and land management techniques, the promotion of diversification strategies and institutional strengthening, in allocated or rented forest land of the Uplands. | The project will deliver global environmental benefits under three GEF Focal Areas, Land Degradation, Biological Diversity and Climate Change. Regarding Land Degradation, the project interventions will reduce land degradation processes in the project area, and will preserve and improve the ecosystem functions and services, including climate and water regulation, and soil conservation. Land and forest use will be enhanced sustainably through the use of combined SLM and SFM techniques, helping to improve livelihoods and offer more opportunities for income generation in a durable way. In relation to Biodiversity, Vietnam has a high level of biological diversity in terms of ecosystems, species and genetic resources. The country is part of the Indo-Burma biodiversity hotspot, including the Greater Annamites Ecoregion. Situated at the junction of two distinct biogeographical zones, the temperate north and the tropical south, this ecoregion encompasses an incredibly broad, diverse and special range of habitats, animals and plants. | 0.83million (LD FA: 0.166million; BD FA: 0.664million) |  | April 2008 |

wb155260

/tmp/in/input.doc

Project ID number will be assigned initially by GEFSEC.